Project Meeting Minutes

Date: 2026.03.16

Time: 11:00 am – 11:30 am

Location: S342, Stokes Building, Glasnevin Campus, Dublin 9

Attendees: Dr. Marissa Condon, Dr. Ali Intizar, Chunyu Long

1. Agenda

- Project planning

- Topology dependence problem

2. Key Discussion Points

- Topic A: Project planning for EEN1101 assignment.

- Topic B: Discuss the topology problem found on the datasets.

- Topic C: Start building the project models.

3.  Decisions Made

- A: Start on a detailed project planning

  - The assignment dues Friday, 10 April 2026.

  - Give the overall project goals.

  - Give specific details of the plan of work to meet the goals and set them out in weekly/fortnightly steps.

- B: PCB topological dependence

  - The dependence of the datasets on the topology is evident from examination of the data.

  - Each dataset in the SI/PI-Database project is associated with a specific PCB topology design. So if one builds an accurate ML surrogate for a specific example, the surrogate would only work well on that topology. Therefore, the initial focus will be on one topology and then extending it to include similar topologies.

  - The project goal is not to replace PCB design workflows. One avenue would be to see how different PCB dimensions and links in a topology affect the output and signal integrity.

  - As the project proceeds, research areas not addressed in the given project but  opportunities for further work can be described in the conclusions.

- C: Start project models

  - Specify the programming tools. (1) Programming language: Python; (2) ML framework: Keras; (3) ML backend: TensorFlow (preliminarily); (4) Development environment: VS code + JupyterNotebook + Anaconda, this setup makes the documentation of work easier.

  - Build the first prototype to show a working design of the system.

  - Submit regular documentation (PDF) with explanations, results and code to the repository and to the supervisor.

4.  Action Items (To be completed by next meeting)

| Task | Deadline | Status |
| --- | --- | --- |
| - Project planning assignment | 10th Apr | In Progress |
| - Build the first model prototype | 30th Mar | In Progress |

5.  Next Meeting

- Date: Monday 30th March at 11am